## Iteration Estimated Effort
Task Name: (Dependencies top to bottom) | [7 empty] | Kole | Joseph | Kevin | Iman | Total
|  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Connect with clients | Project Manager | Kevin | 2 | 2 | 2 | 2 |  |  | 2 |  | 2
[8 empty] | 0 | 0 |  |  | 0
| Create question lists/prepare for client meetings | Developers | Everyone | 2 | 2 | 2 | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 2
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
[8 empty] | 0 |  |  |  | 0
| Interview | Everyone | Everyone | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 4
[8 empty] | 0 |  |  |  | 0
0
0
0
0
0
0
0
Iteration 1: | Decelopment Plans |  |  |  | 10 |  | 21 |  |  |  |  | 0
Design | Create Sitemap | Developers | Everyone | 5 |  | 10 |  | 5 |  | 5 |  | 10
| Create SEO strategy | SEO Specialist | Kole | 1 |  | 2 |  | 2 |  |  |  | 2
| Gather current website info from clients | Project Manager | Kevin | 1 |  | 3 |  |  |  | 3 |  | 3
| Brainstorm pictures, fonts, colors, etc | Everyone | Everyone | 3 |  | 6 |  |  | 3 |  | 3 | 6
0
0
0
0
0
[5 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
Iteration 2: | Finalize Plans |  |  |  | 17 |  | 3 |  |  |  |  | 0
Finalize Plans & Build | Finalize Content | Marketing Strategist | Kevin | 6 | [7 empty] | 0
| Get Logo | UI manager | Iman | 3 | [7 empty] | 0
| Find eCommerce option | Developers | Joseph | 4 |  | 1 |  |  | 1 |  |  | 1
| Find blog option | Developers | Kole | 2 |  | 1 |  | 1 |  |  |  | 1
| Find Calender options | Developers | Kole | 2 |  | 1 |  | 1
0
| Build |  |  |  | 17 |  | 10 |  |  |  |  | 0
| Get Wix ready | Developers | Kevin | 2 | [7 empty] | 0
| Design Pages | UI manager | Iman (everyone) | 15 |  | 10 |  | 10 |  |  |  | 10
0
0
0
| SEO |  |  |  | 3 |  | 2 |  |  |  |  | 0
| Incorporate SEO through Wix | SEO Strategist | Kole | 3 |  | 2 |  | 2 |  |  |  | 2
0
0
Iteration 3: |  |  |  |  | 4 |  | 0 |  |  |  |  | 0
| Get rest of content and images from Taryn and Dona | Marketing Strategist | Kevin | 2 | [7 empty] | 0
| Add plugins on wix | UI manager | Iman | 2 | [7 empty] | 0
0
0
| Build |  |  |  | 8 |  | 0 |  |  |  |  | 0
| Link everything together | Developers | Joseph | 3 | [7 empty] | 0
| Add eCommerce capabilities | Developers | Kevin | 2 | [7 empty] | 0
0
| Launch Site! | Project Manager | Kole | 3 | [7 empty] | 0
0
| SEO |  |  |  | 1 |  | 0 |  |  |  |  | 0
| Create and apply XML map to Google | SEO Strategist | Kole | 1 | [7 empty] | 0
0
Total |  |  |  | 68 | 68 | 44 | 44 | 22.5 | 5.5 | 11.5 | 4.5 | 44